## BurnUp Chart
Sprint | 0 | 1 | 2 | 3 | 4 | 5
Story Points Completed | 0 | 6 | 15 | 28
Total Story Points | 37 | 37 | 37 | 37 | 37 | 37

## Effort Chart
Sprint | 0 | 1 | 2 | 3 | 4 | 5
SM/PM | 14 | 16 | 18 | 22
DEV | 10 | 20 | 22 | 9
QA | 0 | 20 | 11 | 27

## Effort Descriptions
QA | Planning | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Time Taken units: | Day
Manual (Integration) Time Taken | 0 | 14 | 3 | 11
Test Cases Created | 0 | 6 | 8 | 16
Total Effort | 0 | 20 | 11 | 27 | 0 | 0
DEV | Planning | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5
TDD Coding Time Taken | 10 | 14 | 14 | 5
Test Cases Passed | 0 | 6 | 8 | 4
Total Effort | 10 | 20 | 22 | 9 | 0 | 0
PM | Planning | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5
Integration Time Taken | 14 | 14 | 14 | 14
Integration tests passed | 0 | 2 | 4 | 8
Total Effort | 14 | 16 | 18 | 22 | 0 | 0

## do not refer
QA | Plannin | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5
Pass/Fail Test Case | 0 | 25 | 25 | 10
Monitor Test Scripts | 0 | 25 | 25 | 25
Acceptance tests | 0 | 0 | 10 | 25
Monitor Test Results | 0 | 10 | 10 | 25
Total Effort | 0 | 60 | 70 | 85 | 0 | 0
DEV
Feature Dev (35%) | 0 | 35 | 35 | 35
Unit Test (35%) | 0 | 0 | 25 | 35
Monitor results (30%) | 0 | 20 | 30 | 20
Total Effort | 0 | 55 | 90 | 90 | 0 | 0
PM
Project Timeline | 20 | 20 | 20 | 20
Task Allocation | 0 | 20 | 20 | 10
Monitor Team Progress | 0 | 15 | 20 | 20
Feature Test/Dev | 0 | 10 | 10 | 15
Maintain Repository | 20 | 20 | 20 | 20
Total Effort | 40 | 85 | 90 | 85 | 0 | 0